## Month 1 Checklist
Month 1 — Foundations: Vibe Coding, Domain Literacy & First Dataset
UK Flat Racing Ontology Project — detailed checklist, ~3–5 hrs/week over 4 weeks
Legend: set "Done" to Yes as you finish each task. Rows already marked Yes reflect what's been completed together in this project so far.
Progress: | 30 | of | 35 | tasks done ¦ Est. hours: | 12.4 | hrs (~12–20 target)
Week | # | Activity | Details | Est. Hrs | Done | Notes / Resources
Week 1 | 1 | Install Python 3 (Windows) | Download from python.org and run the installer — tick "Add python.exe to PATH" before installing. | 0.25 | Yes | python.org/downloads
| 2 | Install VS Code | Download and install with default settings. | 0.25 | Yes | code.visualstudio.com
| 3 | Confirm Python works from a terminal | Open a terminal and run: python --version — should print a version number, not an error. | 0.1 | Yes
| 4 | Install the Claude Code extension in VS Code | Ctrl+Shift+X to open Extensions, search "Claude Code" (publisher: Anthropic), click Install. | 0.25 | Yes | code.claude.com/docs/en/vs-code
| 5 | Sign in to Claude Code | Click the ✱ spark icon, then Sign in, and complete login in your browser. | 0.1 | Yes
| 6 | Open the racing_project folder in VS Code | File → Open Folder, select the racing_project folder. | 0.1 | Yes
| 7 | Run group1_winners.py successfully | Open the file, click the ▷ Run button, confirm the results print in the terminal panel. | 0.25 | Yes
| 8 | Ask Claude to explain the script | In the Claude Code panel, ask: "explain what group1_winners.py does" — confirms the panel is wired up end to end. | 0.25 | Yes
| 9 | Install Git for Windows | Download and install with default settings. | 0.25 | Yes | git-scm.com
| 10 | Create a GitHub account | Skip if you already have one. | 0.15 | Yes | github.com
| 11 | Configure Git with your name & email | git config --global user.name "..." / git config --global user.email "..." | 0.1 | Yes
| 12 | Initialise a git repository | Run: git init inside the racing_project folder. | 0.1 | Yes
| 13 | Create a .gitignore | Ask Claude to generate a sensible Python .gitignore for this project. | 0.25 | Yes
| 14 | Make your first commit | git add . then git commit -m "Initial commit: Group 1 winners script + data" | 0.15 | Yes
| 15 | Create a GitHub repository | e.g. uk-flat-racing-analytics — create it empty, no README, on github.com. | 0.15 | Yes | github.com/new
| 16 | Connect and push to GitHub | git remote add origin <url> then git push -u origin main | 0.3 | Yes
Week 2 | 17 | Write the first script (winners + favourites) | Store a handful of Group 1 winners and print which started favourite. | 0.5 | Yes
| 18 | Practice the vibe-coding loop again | Ask Claude for one variation, e.g. "print only the upsets" — reinforce ask → check → refine. | 0.5 | Yes
| 19 | Learn: race grades | Note in your own words: Group 1 / 2 / 3 vs Listed vs Class 1–7 handicaps. | 0.5 | Yes | britishhorseracing.com/regulation/glossary-of-race-types/
| 20 | Learn: race distances | Note what furlongs are and roughly how many make up a mile. | 0.25 | Yes
| 21 | Learn: the "going" | Note the going scale: heavy → soft → good to soft → good → good to firm → firm, and why it matters. | 0.25 | Yes
| 22 | Learn: the flat season calendar | Note the season's span and the big fixtures in order: Guineas, Derby/Oaks, Royal Ascot, July meeting, Glorious Goodwood, Ebor, St Leger, Champions Day. | 0.5 | Yes
| 23 | Learn: form figures | Note how to read a form line, e.g. "2-1310". | 0.25 | Yes
| 24 | Checkpoint write-up | In your own words: what is a Group 1 race, and why is it the right population for this project? | 0.5 | Yes
Week 3 | 25 | Split data out of the script | Move race results into data/group1_results_2026.csv so updates never require touching code. | 0.5 | Yes
| 26 | Extend the dataset toward ~20–30 races | Currently at 27 completed 2026 Group 1 races. | 1 | Yes | thestatsdontlie.com/horse-racing/flat/group-1/
| 27 | Decide the dataset's scope going forward | 2026-only, or also pull in 2025 for a bigger sample? Note your decision and why. | 0.25 | Yes
| 28 | Add placeholder columns for later | Add distance, going, and number of runners to the CSV — can stay blank for now, saves rework in month 3. | 0.75 | Yes
| 29 | Spot-check the data | Pick 5 random rows and verify them against a results source — build the habit of checking data, not trusting it. | 0.5 | Yes
| 30 | Add an "add one new race" helper | Ask Claude to write a small function so the CSV can be updated without hand-editing it. | 0.75 | Yes
Week 4 | 31 | Write a README.md | What the project is, how to run group1_winners.py, and where the data comes from. | 0.75 | No
| 32 | Commit and push everything | README, current CSV, and all scripts. | 0.25 | No
| 33 | Save a month 1 snapshot | Re-run group1_winners.py one final time and save/screenshot the output. | 0.15 | No
| 34 | Reflect | Short note: what was confusing this month, what clicked, what you want month 2 to answer. | 0.5 | No
| 35 | Preview month 2 | Skim one beginner RDF/SPARQL explainer — just enough to recognise the vocabulary before month 2 starts. | 0.75 | No