## Month 2 Checklist
Month 2 — Semantic Web Fundamentals: RDF, OWL & SPARQL
UK Flat Racing Ontology Project — detailed checklist, ~3–5 hrs/week over 4 weeks
Legend: set "Done" to Yes as you finish each task. This is a look-ahead — nothing here is expected to be complete yet; Month 1 finishes first.
Progress: | 0 | of | 32 | tasks done ¦ Est. hours: | 17 | hrs (~12–20 target)
Week | # | Activity | Details | Est. Hrs | Done | Notes / Resources
Week 1 | 1 | Learn: what is an RDF triple | Note in your own words: subject–predicate–object, and how it's just a sentence about one fact. | 0.25 | No
| 2 | Learn: URIs, prefixes & namespaces | Note what a URI is and why ex:Frankel is shorthand for a full web address. | 0.25 | No
| 3 | Work through Jena's RDF/SPARQL tutorial (intro) | Read the intro and triples sections — no coding needed yet, just the concepts. | 1.5 | No | https://jena.apache.org/tutorials/
| 4 | Learn: classes, instances & properties | Note the difference: Horse is a class, Frankel is an instance, hasSire is a property. | 0.5 | No
| 5 | Explore the Wikidata Query Service | Open the tool and run its built-in example query to see SPARQL results render. | 0.5 | No | https://query.wikidata.org/
| 6 | Learn basic SPARQL syntax | Note what SELECT, WHERE and a prefix line each do in a query. | 0.5 | No | https://jena.apache.org/tutorials/sparql.html
| 7 | Run a SPARQL query against Wikidata for a real racehorse | Ask Claude to help write a query for a well-known horse's sire/dam; run it in the Query Service. | 0.5 | No | https://query.wikidata.org/
| 8 | Checkpoint: write one of your CSV rows as a triple | Take one row from group1_results_2026.csv and write it out as subject–predicate–object, by hand. | 0.25 | No
Week 2 | 9 | Install Protégé and work through its quickstart tutorial | Download from protege.stanford.edu; follow the "Pizza" quickstart to learn the interface. | 1 | No | https://protege.stanford.edu/
| 10 | Sketch your ontology's classes on paper | Draw boxes for: Horse, Race, Racecourse, RaceEntry, Jockey, Trainer, and how they connect. | 0.5 | No
| 11 | Create the 6 core classes in Protégé | Add Horse, Race, Racecourse, RaceEntry, Jockey, Trainer as OWL classes. | 0.5 | No
| 12 | Add hasSire / hasDam object properties | Define these as relationships between two Horse individuals. | 0.5 | No
| 13 | Add RaceEntry relationships | ofHorse, inRace, riddenBy, trainedBy — RaceEntry is where result/position will live. | 0.5 | No
| 14 | Add data properties on Race | hasDistance, hasGoing, hasClass — literal values rather than links to other classes. | 0.5 | No
| 15 | Save the ontology file and export a diagram | Protégé can export an OntoGraf image — useful for the wall next to your architecture slides. | 0.25 | No
| 16 | Checkpoint: object property vs data property | Explain the difference in your own words, using an example from your own ontology. | 0.5 | No
Week 3 | 17 | Install Apache Jena Fuseki (or set up RDFLib as a lighter start) | Fuseki gives a real local SPARQL endpoint; RDFLib is a lighter Python-only alternative if you'd rather skip a server for now. | 0.5 | No | https://jena.apache.org/documentation/fuseki2/
| 18 | Convert Month 1 CSV rows into RDF triples | Ask Claude to write a script that turns group1_results_2026.csv into triples using your ontology. | 1 | No
| 19 | Load the generated triples into Fuseki / RDFLib | Get your seed dataset into the triple store as real, queryable data. | 0.5 | No
| 20 | Confirm the data loaded | Run a simple "list all races" SPARQL query and check the count matches your CSV. | 0.25 | No
| 21 | Write & run SPARQL query 1 | All races at a given course. | 0.5 | No
| 22 | Write & run SPARQL query 2 | All races over 10+ furlongs. | 0.5 | No
| 23 | Write & run SPARQL query 3 | A question of your own choosing about your data. | 0.5 | No
| 24 | Checkpoint: write a new SPARQL query from scratch | No template this time — answer a question about your data you haven't asked yet. | 0.5 | No
Week 4 | 25 | Write 2 more SPARQL queries | Round out to 5–10 total queries against your own knowledge graph, per the plan's Month 2 deliverable. | 1 | No
| 26 | Document your ontology in a short README | Classes, relationships, and why each exists — future-you will thank present-you. | 0.75 | No
| 27 | Commit and push everything to GitHub | Ontology file, exported diagram, SPARQL queries, and any new/updated scripts. | 0.25 | No
| 28 | Export your Protégé ontology diagram as an image | For your own reference, and optionally to add to the wall print-outs. | 0.25 | No
| 29 | Save a "Month 2 snapshot" | Screenshot one query and its results as a record of where things stood. | 0.25 | No
| 30 | Reflect | Short note: what was confusing this month, what clicked, what you want Month 3 to answer. | 0.5 | No
| 31 | Preview Month 3 | Skim what an ETL pipeline is and how pandas fits between raw data and triples — just enough vocabulary ahead of time. | 0.75 | No
| 32 | Checkpoint (Month 2 success criterion) | Can you write a SPARQL query from scratch to answer a brand-new question, without copying a template? | 0.5 | No